## Project Overview
HOUSE #415 — MEDITERRANEAN STYLE CUSTOM HOME
Beauregard Residential Design ¦ First Floor Plan ¦ 84'1" × 60' Footprint ¦ 3,480 SF Total Heated & Cooled
Large Custom New Build • Two-Story with Attic • Dual Garage • Grand Entry Foyer • Duration: 28 Weeks • SpatialFlow Demo Dataset
PROJECT STATISTICS |  | ALL ROOMS & ZONES — HOUSE #415 FIRST FLOOR
First Floor | 2,581 SF | Room / Zone | Location | SF (Est.) | Ceiling Type | Floor Finish | Key Framing Note | Special Item
Second Floor | 899 SF | Grand Entry Foyer | Center | ~180 | Two-story Special+rotunda | Premium stone tile (300 SF est.) | High-strength door reinforced header | 6×8 Alder Top Treated Wood door
Attic | 234 SF | Great Room | Center-East | ~420 | Two-story coffered | Premium stone tile | Structural header – engineer required | Fireplace, two-story volume
Garage | 938 SF | Kitchen | North-Center | ~220 | Standard 10' | Premium stone tile | Island per plan, pantry adjacent | Counter height per builder
Front Porch | 196 SF + 125 SF steps | Dining Nook | North-West | ~130 | Standard 10' | Premium stone tile | Sliding door to outside | Raised dog ear cabinets
Total H&C | 3,480 SF | Pantry | North-Center | ~60 | Standard | Tile | Entry from kitchen | Shelves per client
Footprint | 84'1" × 60' | Master Bedroom | East | ~320 | Tray ceiling | Carpet (300 SF est.) | Tray ceiling – frame tight as possible | 8×10 windows, 3'-6" walk-in
Style | Mediterranean Custom | Master Bath | East-Center | ~160 | Standard | Eramosa tile (300 SF) + mosaic | Wet bar + storage, raised pedestal | Two shower heads, mosaic detail
Est. Duration | 28 Weeks | Master Closet | East | ~126 | Standard | Carpet (continuation) | 12'6"×10' walk-in | Opt. island? Built-in shelving
Peak Workers | 35 on site | Master Hall | East-Center | ~40 | Standard | Stone tile (continuation) | Connects foyer to master suite | Linear transition
Crane Required | Yes – tower crane | Study / Opt. Bedroom | South-Center | ~200 | Standard 10' | Tile or carpet per client | Can convert to bedroom – closet rough-in | Sliding door, opt. bathroom above
Special Ceilings | 4 unique types | Bathroom (main) | Center | ~80 | Standard | Tile | Adjacent study + entry | Eramosa tile per spec
|  | Laundry | North-West | ~80 | Standard | Tile | W/D, sink, cabinets | Above-garage position
|  | One-Car Garage | North-West | ~380 | Attic/regular floor joists | Concrete slab | 9'×8' door, attic above – insulate | Attic ceiling joists 8'×4" 2×6
★ SPECIAL COMPLEXITY NOTES 1. GRAND ENTRY FOYER: Two-story ceiling — requires scaffolding + chandelier provision 2. GREAT ROOM: Two-story ceiling — structural header engineering required 3. MASTER BEDROOM: Tray ceiling — coordinate with framing 4. FRONT ENTRY: Two-story 'Special' ceiling with rotunda for chandelier 5. COLORED ENTRY PORCH: Flagstone on 4" slab, raised masonry porch 6. ALL LVL BEAMS: Must be engineered and signed off by lumber company 7. ATTIC: 1st floor attic/regular floor joists, insulate |  | Two-Car Garage | South-West | ~558 | Attic/regular floor joists | Concrete slab | 18'×8' door, 2nd floor joists above | Doubled garage beam load points
|  | Colored Entry Porch | South-Center | ~125 steps | Open / covered | Flagstone on 4" slab | Raised masonry porch, 4' columns | 7-8 stair options (3rd optional)
|  | Front Porch | South | 196 SF | Covered | Stone / flagstone | Columns, deck, front entry feature | Mediterranean columns
|  | Attic Space | Over garages | 234 SF | Attic ceiling | None – storage | Access via pull-down or stair | Insulate floor, attic HVAC
|  | Second Floor | Over E portion | 899 SF | Per 2nd floor plan | Per 2nd floor plan | TJI joists, load bearing walls below | 899 SF – separate plan

## Master Schedule
Phase | Activity / Task | Trade | Workers | Priority | Site Zone | Special Note | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
0 · Pre-Con | Permits + plan approvals | GC / Architect | 1 | CRIT | Office | LVL beams need lumber co. sign-off | bar: W1 to W28
0 · Pre-Con | Site survey + stakeout | Surveyor | 2 | CRIT | Full site | 84'1" × 60' footprint + setbacks | bar: W1
0 · Pre-Con | Soil test + geotechnical | Geotech | 2 | HIGH | Full footprint | Mediterranean soil bearing check | bar: W1 to W28
0 · Pre-Con | Lumber co. LVL beam engineering | Lumber co. / SE | 1 | CRIT | Office | ALL LVL beams must be engineered + signed off | bar: W1 to W2
0 · Pre-Con | Temp site office + fencing | GC | 3 | MED | Perimeter | Single entry point – South access | bar: W1 to W28
1 · Site Prep | Clearing + grubbing | Civil | 4 | HIGH | Full site | 84' wide site – significant clear area | bar: W3
1 · Site Prep | Rough grading + cut/fill | Civil | 5 | HIGH | Full footprint | Establish pad elevation | bar: W1 to W28
1 · Site Prep | Temp drainage + erosion control | Civil | 3 | HIGH | Site perimeter | Mediterranean site often sloped | bar: W4
1 · Site Prep | Utility trenching + connections | Civil / Utility | 4 | CRIT | South + North edges | Water, sewer, electric, gas to building | bar: W1 to W28
2 · Foundation | Excavation – full footprint | Civil | 6 | CRIT | Full footprint | 84'×60' – large excavation. Spoil: East | bar: W4 to W5
2 · Foundation | Footings – pour + cure | Concrete | 7 | CRIT | Building perimeter | Stepped footings likely on sloped Med. site | bar: W1 to W28
2 · Foundation | Foundation walls + stem walls | Concrete / Mason | 8 | CRIT | Full perimeter | Garage slab area separate pour | bar: W6 to W7
2 · Foundation | Under-slab plumbing rough-in | Plumber | 4 | CRIT | Kitchen+bath zones | Master bath + main bath + laundry | bar: W1 to W28
2 · Foundation | Slab on grade – garages + entry | Concrete | 7 | CRIT | Garages + porch | 938 SF garage slab. Colored entry porch slab | bar: W7 to W8
2 · Foundation | Main floor slab pour | Concrete | 8 | CRIT | Full first floor | PEAK DAY – large pour. 10-12 mixer trucks | bar: W1 to W28
3 · Framing 1F | Exterior wall framing – 1st floor | Carpenter | 9 | CRIT | Full perimeter | 2×6 exterior walls. 10' plate height | bar: W9 to W10
3 · Framing 1F | Interior wall framing – 1st floor | Carpenter | 8 | HIGH | All interior | 2×4 interior, 2×6 continuous bearing walls | bar: W1 to W28
3 · Framing 1F | LVL beam install – Great Room | Struct. crew | 5 | CRIT | Great Room center | High-strength header – lumber co. engineered | bar: W10
3 · Framing 1F | LVL beam – Grand Entry Foyer | Struct. crew | 5 | CRIT | Entry foyer | Two-story void – engineer signed off | bar: W1 to W28
3 · Framing 1F | LVL beam – garage openings | Struct. crew | 4 | CRIT | Both garages | 18×8 + 9×8 door headers – LVL | bar: W11
3 · Framing 1F | Stair framing – grand stair | Carpenter | 4 | HIGH | Entry foyer | 6'×10' 1/4" radius top treads – Med. style | bar: W1 to W28
3 · Framing 1F | Framing inspections – 1st floor | Inspector | 1 | CRIT | All 1st floor | Before 2nd floor starts | bar: W12
4 · Framing 2F | 2nd floor TJI joist system | Carpenter | 7 | CRIT | Over E portion | TJI joists + 2×6" 15' 5c per builder | bar: W1 to W28
4 · Framing 2F | 2nd floor wall framing (899 SF) | Carpenter | 8 | HIGH | 2nd floor – East | 9' plate height 2nd floor | bar: W13 to W14
4 · Framing 2F | Tray ceiling framing – master | Carpenter | 4 | HIGH | Master Bedroom E | Frame tight as possible per plan note | bar: W1 to W28
4 · Framing 2F | Two-story void framing – foyer | Carpenter | 4 | CRIT | Entry Foyer | Rotunda + chandelier provision – critical | bar: W13 to W14
4 · Framing 2F | Two-story void framing – Gt Room | Carpenter | 4 | CRIT | Great Room | Coffered ceiling structure begins | bar: W1 to W28
4 · Framing 2F | Attic framing – over garages | Carpenter | 4 | HIGH | Garage attic zones | 234 SF attic, 8'×4" 2×6 ceiling joists | bar: W14
4 · Framing 2F | Roof framing – main hip/gable | Carpenter | 8 | CRIT | Full roof | 8:12 hip rafter + 5:12 typical, 2×12 nipple | bar: W1 to W28
4 · Framing 2F | Roof sheathing + felt | Carpenter | 6 | HIGH | Full roof | Internal bracing lead bearing load bearing | bar: W15
4 · Framing 2F | Framing final inspection | Inspector / SE | 1 | CRIT | Full structure | Lumber co. + SE sign-off on all LVL beams | bar: W1 to W28
5 · Exterior | Roof tile – Mediterranean clay | Roofer | 6 | CRIT | Full roof | Clay tile heavy – structural check first | bar: W16 to W17
5 · Exterior | Exterior stucco – 3-coat system | Plasterer | 8 | HIGH | All exterior walls | Mediterranean stucco – lath, scratch, brown, finish | bar: W1 to W28
5 · Exterior | Masonry columns – front porch | Mason | 4 | HIGH | South front porch | Mediterranean columns, deck, front feature | bar: W17 to W18
5 · Exterior | Colored entry porch – flagstone | Mason | 4 | HIGH | South-Center entry | Flagstone on 4" slab, raised masonry porch | bar: W1 to W28
5 · Exterior | Raised masonry porch columns | Mason | 3 | MED | South entry | 4' columns, 2×12 block sizes OR 8" block | bar: W18 to W19
5 · Exterior | Exterior windows + doors | Window installer | 4 | HIGH | All elevations | 6'×8' window units, 6×8 Alder front door | bar: W1 to W28
5 · Exterior | Garage doors – 18×8 + 9×8 | Door installer | 2 | MED | Both garages | Two-car 18'×8', one-car 9'×8' | bar: W19
5 · Exterior | Grand entry door – 6×8 Alder | Door installer | 2 | HIGH | Front entry | Top treated wood alder, reinforced header | bar: W1 to W28
5 · Exterior | Grand stair – exterior masonry | Mason | 3 | HIGH | Front entry porch | 7-8 stair options, 3rd optional per plan | bar: W20 to W21
6 · MEP Rough | Plumbing rough-in – all baths | Plumber | 5 | CRIT | Master+main bath+ldy | Master bath: wet bar, storage, 2 heads | bar: W1 to W28
6 · MEP Rough | HVAC rough-in – all floors | HVAC | 4 | HIGH | All rooms + attic | Attic HVAC zone above garages | bar: W19 to W21
6 · MEP Rough | Electrical rough-in | Electrician | 4 | HIGH | All rooms | 200A+ panel. Chandelier provision – foyer | bar: W1 to W28
6 · MEP Rough | Gas rough-in – fireplace + range | Plumber / Gas | 2 | HIGH | Great Rm + Kitchen | Fireplace gas log + kitchen range | bar: W20
6 · MEP Rough | MEP inspections | Inspector | 1 | CRIT | All | All rough-in signed off before insulation | bar: W1 to W28
7 · Interior | Insulation – walls + attic | Insulator | 4 | HIGH | All interior + attic | R27 walls (2×6), attic insulate per plan | bar: W22
7 · Interior | Drywall – all rooms | Drywaller | 6 | HIGH | All interior | Two-story voids require special scaffold | bar: W1 to W28
7 · Interior | Coffered ceiling – Great Room | Specialty carpenter | 4 | HIGH | Great Room | Two-story coffered – high scaffold required | bar: W23 to W24
7 · Interior | Tray ceiling – Master Bedroom | Carpenter | 3 | HIGH | Master Bedroom | Frame tight per plan note | bar: W1 to W28
7 · Interior | Rotunda ceiling – Grand Entry | Specialty carpenter | 3 | CRIT | Entry Foyer | Two-story special ceiling + chandelier rough | bar: W23 to W24
7 · Interior | Interior plaster – feature walls | Plasterer | 4 | MED | Entry + Great Rm | Mediterranean interior plaster accents | bar: W1 to W28
7 · Interior | Premium stone tile – entry+great+kit | Tile setter | 5 | HIGH | Entry+Great+Kitchen | 300 SF Premium stone floor tile per spec | bar: W24 to W25
7 · Interior | Eramosa tile – master bath | Tile setter | 3 | HIGH | Master Bath | 300 SF Eramosa + mosaic + raised pedestal | bar: W1 to W28
7 · Interior | Eramosa tile – main bath | Tile setter | 2 | MED | Main Bathroom | Eramosa tile per spec | bar: W25
7 · Interior | Carpet – Master Bed + Closet | Flooring | 2 | MED | Master Bed + Closet | 300 SF carpet. Install after tile complete | bar: W1 to W28
7 · Interior | Cabinetry – kitchen + pantry | Cabinet maker | 4 | HIGH | Kitchen + Pantry | Counter height per builder. Pantry shelves | bar: W24 to W25
7 · Interior | Kitchen island installation | Cabinet maker | 2 | MED | Kitchen | Island per plan, counter per builder spec | bar: W1 to W28
7 · Interior | Raised dog ear cabinets – dining | Cabinet maker | 2 | MED | Dining Nook | Raised dog ear style – Med. design | bar: W25
7 · Interior | Master bath – wet bar + storage | Carpenter / Plumber | 3 | MED | Master Bath | Under-basin per builder, mosaic detail | bar: W1 to W28
7 · Interior | Master bath floor – mosaic | Tile setter | 2 | HIGH | Master Bath floor | 300 SF with mosaic area interior only to tile | bar: W25
7 · Interior | Laundry – cabinets + W/D | Carpenter | 2 | LOW | Laundry NW | W/D, sink, shelves | bar: W1 to W28
7 · Interior | Interior doors + hardware | Carpenter | 3 | MED | All rooms | Mediterranean style doors + hardware | bar: W25
7 · Interior | Grand stair – treads + rail | Carpenter | 3 | HIGH | Grand Foyer | 6'×10' 1/4" radius – alder top treads | bar: W1 to W28
7 · Interior | Plumbing trim-out | Plumber | 3 | MED | All baths + kit | 2 heads master shower, fixtures all baths | bar: W26
7 · Interior | Electrical trim-out + chandelier | Electrician | 3 | HIGH | All rooms + foyer | Chandelier in rotunda – high scaffold req. | bar: W1 to W28
7 · Interior | HVAC trim-out + commission | HVAC | 2 | MED | All rooms | Test all zones inc. attic | bar: W26
7 · Interior | Paint – all interior | Painter | 5 | HIGH | All rooms | Two-story rooms need lift/scaffold | bar: W1 to W28
7 · Interior | Study fit-out (opt. bedroom) | Carpenter | 2 | LOW | Study S-Center | Sliding door, opt. closet rough-in if bedrm | bar: W27
8 · Close-Out | Garage slab seal + apron | Concrete | 2 | MED | Both garages | 938 SF garage slab final seal | bar: W1 to W28
8 · Close-Out | Landscaping + front drive | Landscaper | 4 | LOW | All exterior | Mediterranean landscape, drive approach | bar: W27
8 · Close-Out | Final clean | GC | 4 | HIGH | Full building | All trades complete first | bar: W1 to W28
8 · Close-Out | Punchlist + defects | GC + all trades | 5 | HIGH | All | Owner walkthrough | bar: W28
8 · Close-Out | Final inspections | Inspector | 2 | CRIT | Full building | All systems commissioned | bar: W1 to W28
8 · Close-Out | Certificate of Occupancy | Inspector / GC | 1 | CRIT | Full building | CO before handover | bar: W28

## SpatialFlow Input
SPATIALFLOW SPATIAL LAYOUT INPUT — House #415 Mediterranean (84'1" × 60')
LARGEST SITE OF 3 PLANS — Dual garage, two-story voids, clay tile roof, and Mediterranean stucco create complex multi-trade staging requirements
Week | Phase | Activity | Materials Arriving | Volume | Work Zone | Equipment | Storage Zone | Conflict Risk | Spatial Priority Note
1 | Pre-Con | Permits + beam engineering | Documents only | None | Office | None | N/A | LOW | LVL beam package must be with lumber co. week 1 — long lead item
3 | Site Prep | Clearing + grading | None out – debris | High debris | Full 84'×60' site | Bulldozer + grader | Spoil pile: East quadrant | HIGH | Large site. Establish South access road first. Spoil East – away from entry porch zone
4 | Site Prep | Utility trenching | Pipe, conduit, meters | Medium | South + North edges | Mini excavator | North staging strip | MED | Dual service entry for large home. Gas, water, sewer, electric – coordinate
4 | Found. | Excavation | None – debris out | Very High | Full footprint | Large excavator + dump trucks | Spoil: East | CRIT | 84'×60' = 5,040 SF excavation. Many dump truck cycles. Route: East access only
5 | Found. | Footings pour | Ready-mix (trucks) | High | Full perimeter | Concrete pump | Pump: South-Center | CRIT | Large perimeter – multiple pump positions may be needed. South + West setup
6 | Found. | Stem walls + foundation | Concrete block, rebar, concrete | Very High | Full perimeter | Crane / pump | Block: East + South staging | HIGH | Block walls + poured sections. Stage block East, concrete trucks South
7 | Found. | Garage slab pour | Ready-mix concrete | High | Both garages NW+SW | Concrete pump | Pump: West side | HIGH | 938 SF garage slab. West pump position. Keep South approach clear for trucks
8 | Found. | Main floor slab – PEAK | Ready-mix (10-12 trucks) | Very High | Full first floor | Concrete pump ×2 | Two pumps: South + West | CRIT | LARGEST pour of project. 2 pumps needed. All other site access BLOCKED pour day
9 | Framing | Exterior wall framing | Lumber – 2×6 walls | Very High | Full perimeter | Crane | South staging – large lumber | HIGH | 2×6 exterior walls full perimeter. Crane South-Center. Stage lumber South
10 | Framing | LVL beam deliveries | LVL beams (long, heavy, precision) | High | Foyer + Great Rm | Crane | North staging – clear 30ft | CRIT | LVL beams long and heavy. Crane critical. Sequence: Great Room beam → Foyer beam → garage headers
11 | Framing | LVL beam – garage doors | LVL headers 18' + 9' | Medium | Both garages | Crane | West staging | CRIT | 18'×8' two-car header is very long. West crane position for garage
12 | Framing | Stair framing – grand foyer | Stair stringers, treads rough | Medium | Entry foyer center | None | Inside foyer | HIGH | Radius stair in two-story void. Complex framing – lumber co. plans required
13 | Framing | 2nd floor TJI joists | TJI joist bundles (15'5" spans) | High | Over East portion | Crane | East staging – stacked | HIGH | Joists long – East staging 20ft clear. Crane active Wks 13-15
14 | Framing | Two-story void framing | LVL, lumber, scaffold | High | Foyer + Great Room | Scaffold (interior) | Inside – two-story zones | CRIT | Interior scaffold for two-story void framing. Separate from exterior crane
14 | Framing | Roof framing begins | 2×12 rafters, hardware | Very High | Full roof | Crane | South staging – large lumber | CRIT | Crane still active. No staging under crane swing arc
16 | Roof | Clay tile delivery | Clay roof tile (very heavy) | Very High | Full roof | Crane | East + South staging | CRIT | Heaviest roof load of all 3 plans. Clay tile – structural engineer verify before delivery
17 | Exterior | Exterior stucco – scaffold | Stucco mix, lath, full scaffold | Very High | All 4 elevations | Full perimeter scaffold | South staging – stucco mix | HIGH | 3-coat Mediterranean stucco. Scaffold full perimeter. Material route: gaps at South only
18 | Exterior | Front porch columns + masonry | Masonry block, mortar, columns | High | South front porch | Small crane / fork | South-Center staging | HIGH | Mediterranean columns heavy. Small crane or forklift. Scaffold still active on walls
18 | Exterior | Colored entry porch flagstone | Flagstone pallets, mortar | High | South-Center entry | Forklift | South staging – stone pallets | HIGH | Stage South-Center. Heavy stone. Forklift must access entry zone while scaffold active on walls
19 | Exterior | Windows + exterior doors | Window units, Alder front door | Medium | All elevations | Scaffold + small crane | East staging – protected | HIGH | Alder door fragile – deliver just-in-time. Scaffold gaps for window pass-through
20 | Exterior | Grand stair – exterior | Masonry, stone treads | High | South front entry | None | South staging | MED | 7-8 stair options. Third optional. Coordinate with front porch masonry completion
19 | MEP | Plumbing rough-in | Copper + PVC pipe | High | Master Bath + mains | None | Inside – by room | HIGH | Master bath has 2 shower heads, wet bar. Large scope. Start inside while scaffold active outside
20 | MEP | HVAC rough-in | Ductwork, air handlers, units | High | All rooms + attic | Crane for units | North staging – HVAC units | HIGH | Attic HVAC unit over garage – crane to lift. Coordinate with roof completion
21 | MEP | Electrical rough-in | Wire, conduit, panel | High | All rooms | None | Inside – locked | HIGH | 200A+ panel. Chandelier provision in foyer rotunda – rough-in before ceiling close
22 | Interior | Insulation | R27 batts, attic insul. | High | All walls + attic | None | Inside – by area | MED | R27 for 2×6 walls. Attic insulation over garage zone critical for energy
22 | Interior | Drywall – all floors | Drywall sheets (large volume) | Very High | All interior | None | Inside – by floor | HIGH | Large home – big drywall delivery. Two-story rooms need interior scaffold
23 | Interior | Special ceiling work begins | Scaffold, specialty materials | High | Foyer + Great Room | Interior scaffold | Inside – two-story zones | CRIT | Coffered + rotunda + tray ceilings all happening Wks 23-25. Scaffold shared resource – sequence carefully
24 | Interior | Premium stone tile – main | Stone tile (300 SF) | High | Foyer+Great+Kitchen | None | Inside – protected staging | HIGH | Heavy stone tile. Deliver per room. Protect subfloor during delivery
24 | Interior | Eramosa tile – master bath | Eramosa tile, mosaic | High | Master Bath | None | Inside master bath zone | HIGH | Mosaic detail requires specialist. Sequence: tile → pedestal → fixtures
25 | Interior | Carpet – master suite | Carpet rolls (300 SF) | Medium | Master Bed + Closet | None | Inside bedrooms | MED | Install LAST in bedroom sequence. After all other trades complete in zone
26 | Interior | Chandelier – grand foyer | Chandelier (heavy, fragile) | Low | Entry Foyer | Interior scaffold | Inside foyer – protected | CRIT | Chandelier heavy + fragile. Scaffold still needed. Install after drywall + paint complete
27 | Close-Out | Final landscaping | Plants, mulch, drive materials | Medium | All exterior | Skid steer | Exterior perimeter | LOW | Mediterranean landscape. After all exterior work complete. Do not disturb porch areas

## Spatial Conflict Register
SPATIAL CONFLICT RISK REGISTER — House #415 Mediterranean
Largest of 3 plans — dual crane phases, two-story scaffold conflicts, and Mediterranean exterior complexity create multiple critical spatial clashes
Week | Conflict Type | Element A | Element B | Zone | Severity | Resolution
8 | Peak concrete – site lockdown | Main floor slab pour (10-12 trucks) | ALL other site activities | Full site | CRITICAL | Full site lockdown on pour day. Two pumps South + West. No other deliveries. Book concrete plant Friday before
10 | LVL beam sequence | Great Room LVL beam (crane) | Foyer LVL beam (crane) | Center site | CRITICAL | One crane cannot do both in same lift. Sequence: Great Room Mon AM, Foyer Wed AM. Crane repositions between
11 | Crane + garage header conflict | Two-car garage 18' LVL header | One-car garage 9' header | West garages | HIGH | Crane moves to West position for garage headers after main beams. Clear West staging entirely
13 | Crane + joist + scaffold | TJI joists (crane – East) | Interior scaffold (two-story voids) | East + Center | HIGH | Exterior crane lifts joists East. Interior scaffold team works Center simultaneously. Crane arc must not cross scaffold zone
14 | Roof framing + two-story void | Roof framing crane (South) | Interior two-story framing scaffold | S + Center | CRIT | Crane active South for roof. Interior scaffold active Center. Banksman required. Define no-cross zones clearly
16 | Clay tile weight + structure | Clay tile delivery (very heavy) | Roof structural sign-off | Full roof | CRITICAL | Clay tile must NOT be delivered before structural engineer signs off on roof framing. Sequence is non-negotiable
17 | Stucco scaffold vs deliveries | Full perimeter scaffold (3-coat) | All exterior material deliveries | All 4 elevations | HIGH | Designate 2 scaffold gaps at South for material pass-through. All deliveries weeks 17-20 via South gaps only
18 | Porch masonry + active scaffold | Front porch columns + masonry | Exterior stucco scaffold | South elevation | HIGH | South scaffold must have clear bay at porch zone. Masonry crew and stucco crew coordinate daily to avoid collision
18 | Two heavy deliveries – South | Flagstone pallets (entry porch) | Masonry block (porch columns) | South-Center | HIGH | Both arriving same zone same week. Stage flagstone Monday, columns Wednesday. Forklift shared resource – book in advance
19 | Window delivery + scaffold | Window units (fragile) | Active stucco scaffold | All elevations | HIGH | Scaffold gaps for window pass-through. Windows delivered just-in-time. Stucco crew moves to opposite elevation
20 | Exterior stair + porch finish | Grand entry stair masonry | Front porch column completion | South front | MED | Stair below porch level. Sequence: porch columns complete → then stair. Shared South staging area
20 | HVAC unit + roof | HVAC air handler (crane lift to attic) | Roof tile (ongoing) | Roof + North | HIGH | Crane needed for HVAC unit to attic zone. Roof tilers move to South slope while crane lifts North. Coordinate daily
23 | Three special ceilings – scaffold | Coffered ceiling (Great Room) | Rotunda (Foyer) + Tray (Master) | Center + East | CRITICAL | All three specialty ceilings happen weeks 23-25. Interior scaffold is a shared resource. One crew per room. Schedule: Rotunda Mon-Fri Wk23, Coffered Wk24, Tray Wk24 parallel
26 | Chandelier + active paint | Chandelier installation (scaffold) | Interior paint crew | Grand Foyer | HIGH | Paint foyer walls BEFORE chandelier install. Chandelier fragile – no overspray. Sequence: paint → dry → chandelier
14 | LVL beam engineering lead time | Framing schedule (Wk 9 start) | LVL beam delivery (needs eng. approval) | Site | CRITICAL | LVL beams ordered week 1. Lumber co. engineering takes 3-4 weeks. If delayed, framing halts. Track weekly from week 1

## Special Ceiling Tracker
SPECIAL CEILING TRACKER — House #415 Mediterranean
4 unique ceiling types requiring specialist trades, interior scaffold, and careful sequencing with MEP and paint
Room | Ceiling Type | Height | Scaffold Needed | Install Week | Key Requirement from Plan
Grand Entry Foyer | Two-Story 'Special' + Rotunda for Chandelier | Two-story (~20') | YES – tall interior scaffold | Wk 23-24 | Rotunda ceiling with chandelier rough-in provision. Estimate 4 depth to 8' total ceiling collared within tray
Great Room | Two-Story Coffered Ceiling | Two-story (~20') | YES – tall interior scaffold | Wk 23-25 | Two-story coffered ceiling. LVL structural header below. Lumber company engineer and sign off required
Master Bedroom | Tray Ceiling | Standard + tray | Minor – step ladder sufficient | Wk 23-24 | Frame tray ceiling as tight as possible (limited by others). Note on plan: estimate 4 depth to 8' total
Front Entry Porch | Two-Story 'Special' Ceiling (exterior covered) | Two-story covered | YES – exterior scaffold | Wk 17-19 | Two-story special ceiling at front entry. Mediterranean columns support. Coordinate with stucco scaffold
Garage (both) | Attic/Regular Floor Joists – Insulated | Standard garage | None | Wk 22 | 8'×4" 2×6 attic ceiling joists 2×6 TJI, insulate. Second floor joists above two-car garage
Dining Nook | Standard 10' Plate Height | 10' | None | Wk 22-23 | Standard ceiling. First floor wall/plate height at 10'
Kitchen | Standard 10' | 10' | None | Wk 22-23 | Standard. Counter height per builder – ceiling not special
Study / Opt. Bed | Standard 10' | 10' | None | Wk 23 | Standard. Sliding door to exterior. If converted to bedroom, closet rough-in above
Master Bath | Standard with bulkhead | Standard | None | Wk 23 | Wet bar + storage under basin per builder. Ceiling standard with possible bulkhead for shower