## Project Overview
CONSTRUCTION PROJECT SCHEDULE
Plan 2788 — Santa Fe Style Residential ¦ 2,788 SF Heated ¦ 870 SF Garage ¦ 870 SF Portal
Randall Southwest Plans • Total Project Duration: 20 Weeks • SpatialFlow Demo Dataset
PROJECT STATISTICS |  | ROOMS / ZONES IDENTIFIED FROM PLAN 2788
Heated Area | 2,788 SF | Zone | Location on Plan | Key Finish | Spatial Notes
Garage Area | 870 SF | Living Room | Center | Hardwood / Diamond | Entertainment wall, sliding doors
Portal Area | 870 SF | Dining Room | Center-West | Hardwood / Diamond | Adjacent kitchen, open plan
Total Roof | 4,628 SF | Kitchen / Brkfst | West-Center | Tile floor, vigas | Melamine shelves, gas BBQ nearby
Est. Duration | 20 Weeks | Master Bedroom | South-West | Carpet, vigas | M.B. bath attached, exterior access
Est. Workers | Peak 28 | Bedroom 2 | East | Carpet | Closet, adjacent bath
Cranes Needed | 1 Mobile | Bedroom 3 | South-East | Carpet | Roof/shelf storage above
Phases | 6 | Double Garage | South-Center | Insulate/drywall | Car stop, gas door opener
|  | Single Car Garage | East | Tile floor | Drywall, paint
|  | Rear Portal | West | Concrete | Peeled latilla railing, custom gate
|  | Front Portal | North-East | Flagstone/concrete | 8" vidrio block wall
|  | Rear Courtyard | West | Stained concrete | Block pilaster, courtyard wall
|  | BBQ / Bar Area | West-Exterior | Concrete block | Gas BBQ, bar framing
|  | Entr / Entry | Center-East | Stone, bone tile | Glass w/ cultured stone surround

## Master Schedule
Phase | Activity / Task | Trade | Workers | Priority | Site Zone | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20
1 · Site Prep | Mobilisation & temp facilities | GC | 4 | HIGH | Perimeter | bar: Wk 1 to Wk 20
1 · Site Prep | Erosion control / temp fencing | Civil | 3 | HIGH | Full perimeter | bar: Wk 1
1 · Site Prep | Stake out / surveying | Surveyor | 2 | CRIT | Full site | bar: Wk 1 to Wk 20
1 · Site Prep | Utility locates & connections | Civil / Utility | 3 | CRIT | North edge | bar: Wk 2
2 · Foundation | Excavation & grading | Civil | 5 | CRIT | Full footprint | bar: Wk 1 to Wk 20
2 · Foundation | Footings – pour & cure | Concrete | 6 | CRIT | Building edge | bar: Wk 3
2 · Foundation | Stem walls / slab prep | Concrete / Mason | 8 | CRIT | Center | bar: Wk 1 to Wk 20
2 · Foundation | Slab on grade – pour & cure | Concrete | 6 | CRIT | Full footprint | bar: Wk 5
2 · Foundation | Under-slab plumbing rough-in | Plumber | 3 | HIGH | Kitchen/Baths | bar: Wk 1 to Wk 20
3 · Structure | Block wall construction (8" vidrio & CMU) | Mason | 8 | CRIT | Perimeter + portals | bar: Wk 6 to Wk 8
3 · Structure | Peeled latilla / viga beam delivery | GC | 2 | HIGH | Staging – West | bar: Wk 1 to Wk 20
3 · Structure | Roof framing – vigas & decking | Carpenter | 6 | CRIT | Full roof | bar: Wk 8 to Wk 9
3 · Structure | Roof sheathing & felt paper | Carpenter | 4 | HIGH | Full roof | bar: Wk 1 to Wk 20
3 · Structure | Exterior door / window rough opens | Carpenter | 4 | MED | All elevations | bar: Wk 8 to Wk 9
3 · Structure | Garage framing & car stop | Carpenter | 4 | MED | South-Center | bar: Wk 1 to Wk 20
4 · MEP Rough | Plumbing rough-in (all baths + kitchen) | Plumber | 4 | CRIT | Baths/Kitchen | bar: Wk 9 to Wk 10
4 · MEP Rough | HVAC rough-in & duct work | HVAC | 3 | HIGH | Attic / all rooms | bar: Wk 1 to Wk 20
4 · MEP Rough | Electrical rough-in | Electrician | 3 | HIGH | All rooms | bar: Wk 9 to Wk 10
4 · MEP Rough | Gas line rough-in (BBQ, fireplace) | Plumber / Gas | 2 | HIGH | West exterior + LR | bar: Wk 1 to Wk 20
4 · MEP Rough | Inspections – MEP rough | Inspector | 1 | CRIT | Full interior | bar: Wk 11
5 · Exterior | Stucco / exterior plaster | Plasterer | 6 | HIGH | All exterior walls | bar: Wk 1 to Wk 20
5 · Exterior | Roof tile / roofing system | Roofer | 4 | CRIT | Full roof | bar: Wk 10 to Wk 11
5 · Exterior | Flagstone – front portal & hearth | Mason | 3 | MED | NE Portal / LR | bar: Wk 1 to Wk 20
5 · Exterior | Courtyard block wall & gate | Mason | 3 | MED | West courtyard | bar: Wk 12 to Wk 13
5 · Exterior | Concrete flatwork – portals & drives | Concrete | 4 | MED | West + NE + South | bar: Wk 1 to Wk 20
5 · Exterior | Exterior doors & custom gate inst. | Carpenter | 3 | MED | All entries | bar: Wk 13
5 · Exterior | BBQ / bar framing & finish | Mason / GC | 3 | LOW | West exterior | bar: Wk 1 to Wk 20
6 · Interior | Insulation – walls & garage | Insulator | 3 | HIGH | All interior | bar: Wk 12
6 · Interior | Drywall hang & tape – type X garage | Drywaller | 4 | HIGH | Garage | bar: Wk 1 to Wk 20
6 · Interior | Interior plaster / diamond finish walls | Plasterer | 5 | HIGH | LR/Dining/Entry | bar: Wk 13 to Wk 14
6 · Interior | Hardwood floor – LR & Dining | Flooring | 3 | MED | Center | bar: Wk 1 to Wk 20
6 · Interior | Tile floor – kitchen, baths, entry | Tile setter | 3 | MED | Kitchen/Baths/Entr | bar: Wk 15 to Wk 16
6 · Interior | Carpet – 3 bedrooms | Flooring | 2 | MED | Beds 1,2,3 | bar: Wk 1 to Wk 20
6 · Interior | Cabinetry – kitchen, baths, shelves | Cabinet maker | 3 | MED | Kitchen/Baths | bar: Wk 15 to Wk 16
6 · Interior | Interior doors & hardware | Carpenter | 2 | MED | All rooms | bar: Wk 1 to Wk 20
6 · Interior | Plumbing trim-out (fixtures/faucets) | Plumber | 2 | MED | All baths + kit | bar: Wk 17
6 · Interior | Electrical trim-out & panel | Electrician | 2 | MED | All rooms | bar: Wk 1 to Wk 20
6 · Interior | HVAC trim-out & commissioning | HVAC | 2 | MED | Full interior | bar: Wk 17
6 · Interior | Paint – interior all rooms | Painter | 4 | MED | All interior | bar: Wk 1 to Wk 20
6 · Interior | Fireplace – cultured stone surround | Mason | 2 | MED | Living Room | bar: Wk 16
6 · Interior | Entertainment center built-in | Carpenter | 2 | LOW | Living Room | bar: Wk 1 to Wk 20
6 · Interior | Melamine shelving – kitchen | Carpenter | 1 | LOW | Kitchen | bar: Wk 18
6 · Interior | Final clean & punchlist | GC | 4 | HIGH | Full interior | bar: Wk 1 to Wk 20
6 · Interior | Final inspections & CO | Inspector / GC | 2 | CRIT | Full site | bar: Wk 20

## SpatialFlow Input
SPATIALFLOW SPATIAL LAYOUT INPUT — Plan 2788
This sheet drives the AI spatial reasoning engine: site zone assignments, material staging, equipment placement, conflict flags
Week | Phase | Activity | Materials Arriving | Volume / Weight | Work Zone (compass) | Equipment Needed | Site Storage Zone | Conflict Risk | Spatial Priority Note
1 | Site Prep | Mobilisation | Temp office, fencing, signs | Low | Perimeter | Pickup trucks | North edge – site entrance | LOW | Establish single entry/exit point at north
1 | Site Prep | Survey & stakeout | Survey equipment | Negligible | Full site | None | N/A | LOW | Clear full site sightlines required
2 | Site Prep | Utility connections | Pipe, conduit, meters | Medium | North boundary | Mini excavator | North staging strip | MED | Keep north edge clear for utility trucks
2 | Foundation | Excavation | None arriving | None | Full footprint | Excavator + dump trucks | Spoil pile – East quadrant | HIGH | Dump truck route: East access road. Spoil pile must not block crane zone
3 | Foundation | Footings pour | Ready-mix concrete (trucks) | High | Building perimeter | Concrete pump | Pump: South-Center | CRIT | Continuous truck queue needed. Route: South entry → pump → exit East
4 | Foundation | Slab prep + sub-slab | Rebar, gravel, poly sheeting | High | Full footprint | None | Rebar: South staging | HIGH | Rebar bundles heavy — stage adjacent to footprint south side
4 | Foundation | Under-slab plumbing | PVC pipe, fittings | Medium | Kitchen + baths | None | Plumbing materials: Center-W | MED | Small materials — store inside future footprint boundary
5 | Foundation | Slab pour | Ready-mix concrete (trucks) | Very High | Full footprint | Concrete pump | Pump: South-Center | CRIT | PEAK concrete day. All other deliveries STOP. Full site access for trucks
6 | Structure | CMU / block walls | Concrete block pallets (heavy) | Very High | All elevations | Block crane / forklift | Block staging: East + South | CRIT | Forklift must access all wall faces. Stage blocks per elevation to minimise carries
7 | Structure | Viga / latilla delivery | Peeled log vigas (long, heavy) | High | Roof zone | Crane or boom truck | West staging – long load area | HIGH | Vigas up to 20ft long. West staging must be clear 30ft. Overhead clearance critical
8 | Structure | Roof framing | Lumber, hurricane ties, nails | Medium | Roof level | Crane / material lift | Lumber: South staging | HIGH | Crane critical – position South-Center to reach all roof zones
9 | Structure | Roof sheathing | OSB/decking, felt paper | Medium | Roof | Crane | Roof materials: South staging | MED | Crane still active. No material staging under crane swing arc
9 | MEP Rough | Plumbing rough-in | Copper/PVC pipe, fittings | Medium | Baths + Kitchen | None | Inside building footprint | MED | Materials stored inside – protect from weather
9 | MEP Rough | HVAC rough-in | Duct, equipment, insulation | High | Attic / all rooms | Lift / crane | HVAC equip: North staging | HIGH | HVAC units heavy. Stage North – away from active block work
10 | MEP Rough | Electrical rough-in | Wire, conduit, panel | Medium | All rooms | None | Inside building | MED | Coordinate with plumber – no ceiling conflict
10 | MEP Rough | Gas rough-in | Black iron pipe, fittings | Low | West ext + LR | None | West staging | HIGH | BBQ + fireplace gas lines. Pressure test before close-up
11 | Exterior | Stucco / plaster | Stucco mix, lath, scaffold | High | All exterior | Scaffold (tube & clamp) | Scaffold storage: South | HIGH | Scaffold around full perimeter. Worker path: perimeter walkway only
11 | Exterior | Roof tile | Roof tile pallets | Very High | Roof | Crane | Tile staging: South-East | CRIT | HEAVIEST roof load. Stage East – crane lifts to roof. Do NOT stage under eave
12 | Exterior | Flagstone – portal/hearth | Flagstone pallets | High | NE Portal + LR | Forklift | Stone: NE corner staging | MED | Small area – stage directly adjacent to work zone
12 | Exterior | Courtyard wall | CMU block, mortar | Medium | West courtyard | None | West exterior | MED | West courtyard enclosed – materials must enter via West gate
13 | Exterior | Concrete flatwork | Ready-mix concrete | Medium | Portals + drives | Concrete pump | Pump: accessible all portals | MED | 3 separate pour areas: front portal, rear portal, drives
13 | Interior | Insulation | Batt insulation rolls | Low | All interior | None | Inside building | LOW | Lightweight. Store inside. No conflict
14 | Interior | Drywall – garage | Drywall sheets (type X) | Medium | Garage | None | Garage interior staging | MED | Type X fire rated for garage. Keep dry
15 | Interior | Interior plaster | Plaster mix, scaffold | Medium | LR/Dining/Entry | Interior scaffold | Interior – center | HIGH | Interior scaffold conflicts with flooring crew – sequence carefully
15 | Interior | Hardwood flooring | Hardwood planks (acclimatise) | Medium | LR + Dining | None | Inside – acclimatise 72hr | HIGH | Must acclimatise ON SITE 72hrs before install. Stage inside Week 14
15 | Interior | Cabinetry | Cabinet boxes, hardware | Medium | Kitchen + Baths | None | Inside – Kitchen zone | MED | Deliver after plaster dry. Sequence: cabs → tile → plumbing trim
16 | Interior | Tile – floor | Tile, thinset, grout | Medium | Kitchen/Baths | None | Inside – bath zones | HIGH | Wet trade – allow 48hr cure before traffic
16 | Interior | Carpet | Carpet rolls | Medium | Beds 1,2,3 | None | Bedrooms – last | MED | Install LAST in bedroom sequence after all other trades done
16 | Interior | Fireplace surround | Cultured stone, mortar | Low | Living Room | None | LR – fireplace zone | MED | Protect hardwood during stone install
17 | Interior | Plumbing trim-out | Fixtures, faucets, toilets | Medium | All baths + kit | None | Inside – staged by room | MED | Fixtures fragile – deliver just-in-time Week 17
17 | Interior | Electrical trim-out | Devices, fixtures, panel | Low | All rooms | None | Inside | MED | Panel energised this week – safety protocols
17 | Interior | Paint – interior | Paint, primer, drop sheets | Low | All rooms | None | Inside – paint storage cool | HIGH | SEQUENCE CRITICAL: paint before trim, after tile
18 | Interior | Melamine shelving | Melamine panels, hardware | Low | Kitchen | None | Inside – kitchen | LOW | Final cabinet item – after all appliances rough positioned
19 | Interior | Final clean | Cleaning supplies | Negligible | Full interior | None | N/A | LOW | All trades complete before clean begins
20 | Interior | Final inspection / CO | None | None | Full site | None | N/A | CRIT | Certificate of Occupancy. All systems commissioned and tested

## Materials & Deliveries
MATERIALS & DELIVERIES SCHEDULE — Plan 2788
Week | Material | Quantity (Est.) | Supplier Type | Delivery Vehicle | Unload Zone | Storage Location | Notes
1 | Temp fence panels | 200 LF | Rental | Flatbed | Site perimeter | Installed immediately | Set before any work begins
2 | Excavation equipment | 1 excavator | Rental | Lowboy trailer | South access | South staging | Deliver Monday AM wk 2
3 | Ready-mix concrete – ftgs | 18 CY | Ready-mix plant | Mixer trucks ×3 | South pump zone | Pour direct – no storage | Morning pour, 3 trucks sequential
4 | Rebar (footings+slab) | 4 tons | Steel supplier | Flatbed | East access | East staging area | Bundle by use zone. Heavy – forklift req.
4 | PVC pipe – sub-slab | 200 LF + fittings | Plumbing supplier | Van/pickup | North entry | Inside footprint | Small – stage inside
5 | Ready-mix – slab | 42 CY | Ready-mix plant | Mixer trucks ×6 | South pump zone | Pour direct | PEAK DAY – 6 trucks. All other access blocked
6 | CMU block (8" + 6") | 18 pallets | Masonry supplier | Flatbed + fork | East + South | Staged by elevation | Heaviest delivery. Forklift essential
7 | Vigas (peeled latilla) | 30 pcs × 16-20ft | Timber supplier | Flatbed long load | West – long load | West staging – clear 30ft | Requires long-load permit. Crane assist
7 | Lumber – roof framing | 8,000 BF | Lumber yard | Flatbed | South staging | South staging stacked | Tarped – rain protection
8 | OSB sheathing | 120 sheets | Lumber yard | Flatbed | South staging | South staging | Lift to roof by crane
9 | Copper/PVC plumbing pipe | 500 LF + fittings | Plumbing supply | Van | North entry | Inside – by room | Stage per room for efficiency
9 | HVAC ductwork + units | 2 AHUs + ducts | HVAC supplier | Box truck | North staging | North staging | Units heavy – stage near crane reach
9 | Electrical wire + panel | Full rough pkg | Electrical supply | Van | North entry | Inside – locked | Panel: 200A. Lock storage required
10 | Black iron pipe – gas | 150 LF + fittings | Plumbing supply | Van | West entry | West exterior | BBQ + fireplace lines
11 | Scaffold – tube & clamp | Full perimeter | Rental | Flatbed | South | Erected immediately | Full perimeter scaffold. 3-4 lifts
11 | Stucco mix + lath | 8 tons mix | Masonry supply | Flatbed | South staging | South – covered pallet | Keep dry. Rotate stock FIFO
11 | Roof tile pallets | 22 pallets | Roofing supplier | Flatbed | East staging | East – crane lifts to roof | Heaviest roof load. Structural check req.
12 | Flagstone pallets | 4 pallets | Stone supplier | Flatbed | NE corner | NE corner – adjacent work | Flagstone for portal + hearth
13 | Ready-mix – flatwork | 12 CY | Ready-mix plant | Mixer ×2 | Multiple portals | Pour direct | 3 separate pours: portals + drives
14 | Drywall – type X | 80 sheets | Drywall supplier | Flatbed | Garage entry | Inside garage | Type X fire-rated for garage only
14 | Hardwood flooring | 1,100 SF | Flooring supplier | Box truck | North entry | Inside – LR zone (acclim.) | MUST acclimatise 72hr before install
15 | Tile – floor (all) | 650 SF + grout | Tile supplier | Box truck | North entry | Inside – by room | Kitchen, baths, entry – stage per room
15 | Cabinetry | Full kitchen set | Cabinet maker | Box truck | North entry | Inside – kitchen | Deliver after plaster dry
16 | Carpet + pad | 950 SF | Flooring supplier | Box truck | North entry | Inside – bedrooms | Last floor install – after all others
16 | Cultured stone – fireplace | 1 pallet | Stone supplier | Pickup | LR entry | Inside – LR | Small delivery – protect hardwood
17 | Plumbing fixtures | Full trim set | Plumbing supply | Van | North entry | Inside – by bathroom | Fragile. Just-in-time delivery only
17 | Electrical fixtures | Full trim set | Electrical supply | Van | North entry | Inside – locked | After panel energised
17 | Paint + primer | 60 gallons | Paint supplier | Pickup | North entry | Inside – cool storage | Flammable – ventilated storage req.
18 | Melamine shelving | 1 kitchen set | Cabinet maker | Van | North entry | Inside – kitchen | Final interior item
20 | Landscaping / final grade | Sod, plants, gravel | Landscape supply | Pickup/trailer | South entry | Exterior – all sides | After CO – site restoration

## Spatial Conflict Register
SPATIAL CONFLICT RISK REGISTER — SpatialFlow Output
Identifies weeks/zones where multiple trades or deliveries compete for the same site space
Week | Conflict Type | Trade/Activity A | Trade/Activity B | Conflict Zone | Severity | Recommended Resolution
5 | Access conflict | Concrete pump + mixer trucks | ALL other site access | South + East access | CRITICAL | Full site lockdown on pour day. No other deliveries Wk 5
6 | Zone overlap | CMU block staging (East+South) | Excavator demob route | East + South | HIGH | Demob excavator before block delivery. Sequence: Mon demob → Wed blocks
7 | Long-load access | Viga delivery (20ft flatbed) | Lumber delivery (flatbed) | West + South | HIGH | Schedule on different days. Vigas Mon, Lumber Wed. Clear West 30ft
8 | Crane swing arc | Crane (South-Center position) | Lumber staging (South) | South quadrant | HIGH | Stage lumber East of crane centerline. Mark no-go arc with cones
9 | Trade stack | Plumber (rough-in) | HVAC (rough-in) | Kitchen + attic | HIGH | Plumber: ground floor first. HVAC: attic first. Daily coordination mtg
9 | Trade stack | Electrician (rough-in) | Plumber (rough-in) | All interior walls | HIGH | Assign zones by room. Electrician: East half. Plumber: West half Wk 9
11 | Scaffold vs access | Perimeter scaffold (erected) | Stucco material deliveries | All exterior faces | MED | Designate scaffold bay gaps at South for material pass-through
11 | Crane + scaffold | Crane (roof tile lifts) | Scaffold (perimeter) | East elevation | HIGH | Lift roof tiles before East scaffold bay erected. Sequence critical
13 | Multi-pour conflict | Concrete flatwork (3 locations) | Interior trades moving in | Portals + interior | MED | Pour portals first. Interior trades enter after 24hr cure
15 | Wet + dry conflict | Interior plasterer | Hardwood flooring crew | LR + Dining | HIGH | Plaster fully dry (7 days min) before hardwood. Plaster Wk 14, floor Wk 15+
15 | Trade congestion | Cabinetry install | Tile setter (floor) | Kitchen | HIGH | Cabs first → tile up to cab bases → plumbing trim. Strict sequence
16 | Floor protection | Cultured stone (fireplace) | Hardwood floor (installed) | Living Room | MED | Protect hardwood with ram board during stone work. Inspect daily
17 | Multi-trade peak | Plumber + Electrician + HVAC | Painter | All rooms | HIGH | Paint AFTER all rough trim complete. No wet paint with live trades
17 | Flammable storage | Paint storage (interior) | Electrical energising | Interior – all | CRITICAL | Paint stored in ventilated room. No energising in paint storage room