## Project Overview
RENOVATION & ADDITION CONSTRUCTION SCHEDULE
Mixed-Use Residential Renovation ¦ 68'-2" × 43'-0" Footprint ¦ Existing Structure + New Addition
⚠ RENOVATION PROJECT — Existing Occupants Must Vacate • Duration: 22 Weeks • SpatialFlow Demo Dataset
PROJECT FACTS |  | ZONES / ROOMS IDENTIFIED FROM PLAN
Project Type | Renovation + Addition | Zone / Room | Location | Status | Key Structural Note | Key Finish Note | Fire Rating
Footprint | 68'-2" × 43'-0" | Garage | South-West | EXISTING | 4" conc. slab on 6" crushed stone, 1% slope | Gas-proof ceiling & walls | 1½ hr ceiling (C1 type)
Parking Levels | 3 (ground + above) | Covered Porch (main) | North-West | EXISTING | 6×6 posts, Timberstrand beam No.6 | 3'-6" high guard | N/A
Bedrooms | 2 (existing) | Parking Level 1 | West-Center | EXISTING | TJI @ 16" OC, 8" conc. block wall | 1½ hr fire rated ceiling | 1 hr
Est. Duration | 22 Weeks | Parking Level 2 | West-Center | EXISTING | Timberstrand beam, solid bearing | Outline of floor above | 1 hr
Peak Workers | 20 on site | Parking Level 3 | West | EXISTING | HSS 3.5" steel post, 0.188" thick | Ledger connection detail | N/A
Structural Work | Major – beams/posts | Staircase | Center | EXISTING | Central stair, DN to parking | Existing joists remain | N/A
Occupied During? | NO – must vacate | Bedroom 1 | North-Center | EXISTING+RENO | 160 SF room, exist. joists | Close-up exist. openings, face brick | N/A
|  | Bedroom 2 | Center-East | EXISTING+RENO | Exist. joists, new window | Close-up exist. window | N/A
⚠ RENOVATION CRITICAL DIFFERENCES vs NEW BUILD 1. Existing structure must be assessed before any work 2. Asbestos / hazmat survey required before demolition 3. Structural engineer must verify existing beams for new loads 4. Face brick matching is critical — note 'match exist' on plan 5. Existing porch, stairs, steel guard to remain — protect during work 6. Gas-proof garage ceiling must be maintained throughout |  | Bathroom | Center | EXISTING | W/D location adjacent | Standard bath finishes | N/A
|  | Storage / Utilities | Center | EXISTING | TJI joists | New window 1/2"×1/4" | N/A
|  | Existing Porch | Center-East | EXISTING–KEEP | Conc. stair existing – remain | Existing – protect | N/A
|  | Covered Porch (East) | East | EXISTING–KEEP | Exist. ceiling/floor assembly above | New concrete stairs added | N/A
|  | Kitchen | North-East | RENOVATION | Remove exist. stairs, new floor assembly | New floor per Design No. F4a | 45 min (STC 50)
|  | Dining | Center-East | RENOVATION | Replace beam w/ 3½×9½" 2.0E Parallam #3 | Existing finishes adapt | N/A
|  | Living Room | East | EXISTING+RENO | New window, exist. ceiling/floor above | New window installation | N/A
|  | Closet | Center-East | EXISTING | Adjacent bedroom | Standard | N/A
|  | Fire-Escape Stairs | South-East | EXISTING–KEEP | Existing steel stairs – remain | Existing steel guard remain | Code required
|  | New Brick Post | South-East | NEW | Remove exist., build new 12"×12" on same foundation | Face brick to match | N/A
|  | New Concrete Stairs | East-Covered | NEW | New concrete stair at covered porch | Concrete finish | N/A

## Master Schedule
Phase | Activity / Task | Trade | Workers | Priority | Site Zone | Reno Note | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22
0 · Pre-Con | Hazmat / asbestos survey | Hazmat consultant | 2 | CRIT | Full interior | MANDATORY before demo | bar: Wk1 to Wk22
0 · Pre-Con | Structural engineer assessment | Struct. Engineer | 2 | CRIT | All beam/post locs | Verify existing beams for new loads | bar: Wk1
0 · Pre-Con | Permit applications | GC / Architect | 1 | CRIT | Office | All permits before mobilisation | bar: Wk1 to Wk22
0 · Pre-Con | Occupant vacate + contents removal | Owner / Movers | 4 | CRIT | Full building | Building must be empty before demo | bar: Wk1
0 · Pre-Con | Temporary protection – exist. porch+stairs | GC | 3 | HIGH | East porch + stairs | Protect items noted 'remain' | bar: Wk1 to Wk22
1 · Demo | Remove existing stairs (kitchen) | Demo crew | 4 | CRIT | Kitchen – NE | Plan notes: remove exist. stairs | bar: Wk3
1 · Demo | Remove existing floor assembly (kit) | Demo crew | 4 | CRIT | Kitchen floor zone | New floor assembly to design F4a | bar: Wk1 to Wk22
1 · Demo | Close-up exist. window openings | Mason / Carpenter | 3 | HIGH | Bedroom 1 + 2 | Face brick to match existing | bar: Wk3 to Wk4
1 · Demo | Remove exist. beam – dining | Struct. crew | 3 | CRIT | Dining – E | Replace w/ Parallam beam No.3 | bar: Wk1 to Wk22
1 · Demo | Remove exist. brick post – SE | Mason | 2 | HIGH | South-East corner | Rebuild new 12"×12" on same fdn | bar: Wk4
1 · Demo | Hazmat abatement (if found) | Hazmat contractor | 3 | CRIT | As identified | Stop-work until cleared if found | bar: Wk1 to Wk22
2 · Structure | Install new Parallam beam No.3 – dining | Struct. crew | 4 | CRIT | Dining zone | 3½×9½" 2.0E Parallam. Temp shores req. | bar: Wk5
2 · Structure | Timberstrand beam No.6 – porch | Carpenter / Struct | 4 | CRIT | North-West porch | 2-1 3/4×11 7/8×1.7E beam | bar: Wk1 to Wk22
2 · Structure | HSS steel post installation | Steel / Struct. | 3 | CRIT | West parking lvl | 3.5" HSS, 0.188" thick, base plate | bar: Wk5 to Wk6
2 · Structure | TJI floor joists – parking/storage | Carpenter | 4 | HIGH | West levels | 11 7/8" TJI @ 16" OC | bar: Wk1 to Wk22
2 · Structure | New ledger connection – kitchen | Carpenter | 3 | HIGH | Kitchen – NE | 2-2×10 ledger, 2 rows 1½" dia bolts | bar: Wk6
2 · Structure | New concrete block wall – parking | Mason | 4 | HIGH | West parking | 8" conc. block, design B1b, SG-8 | bar: Wk1 to Wk22
2 · Structure | Structural inspections | Inspector + SE | 1 | CRIT | All structural | Engineer sign-off before close-up | bar: Wk8
3 · Exterior | New floor assembly – kitchen | Carpenter | 3 | CRIT | Kitchen | Per Design No. F4a – 45min fire rating | bar: Wk1 to Wk22
3 · Exterior | Face brick – bedroom windows | Mason / Bricklayer | 3 | HIGH | Bedroom 1+2 facade | Match existing brick exactly | bar: Wk9 to Wk10
3 · Exterior | New windows – bedroom 1+2 + living | Window installer | 2 | HIGH | N facade + E | New window units to match exist. size | bar: Wk1 to Wk22
3 · Exterior | New concrete stairs – east porch | Concrete crew | 3 | MED | East covered porch | New conc. stair at exist. porch | bar: Wk10
3 · Exterior | New brick post – SE corner | Mason | 2 | HIGH | South-East | 12"×12" on same existing foundation | bar: Wk1 to Wk22
3 · Exterior | Garage slab – patch + seal | Concrete | 2 | MED | Garage | 4" slab on 6" crushed stone, 1% slope | bar: Wk11
3 · Exterior | Gas-proof ceiling repair – garage | GC / Drywall | 2 | CRIT | Garage | Must maintain gas-proof rating throughout | bar: Wk1 to Wk22
3 · Exterior | Guard rails – parking (3'-6" high) | Metal fabricator | 2 | HIGH | North-West porch | 3'-6" high guard per plan | bar: Wk11
4 · MEP Rough | Plumbing rough-in – bathroom + W/D | Plumber | 3 | HIGH | Center bathroom | W/D hookup adjacent bathroom | bar: Wk1 to Wk22
4 · MEP Rough | Electrical rough-in – all areas | Electrician | 3 | HIGH | All rooms | Panel upgrade likely required | bar: Wk10 to Wk11
4 · MEP Rough | HVAC rough-in | HVAC | 2 | HIGH | All rooms | Coordinate with new floor assembly | bar: Wk1 to Wk22
4 · MEP Rough | Gas line – garage (gas-proof zone) | Plumber / Gas | 2 | CRIT | Garage | Gas-proof ceiling critical – inspect | bar: Wk12
4 · MEP Rough | MEP inspections | Inspector | 1 | CRIT | All | Before any close-up or insulation | bar: Wk1 to Wk22
5 · Interior | Insulation – walls + 1½hr ceiling | Insulator | 3 | CRIT | Parking + garage | 1½ hr C1 type ceiling – fire rated | bar: Wk13
5 · Interior | Drywall – all interior | Drywaller | 4 | HIGH | All interior | Type X where fire-rated required | bar: Wk1 to Wk22
5 · Interior | Kitchen fit-out – new floor finish | Flooring | 2 | HIGH | Kitchen | Achieve 45min fire + STC 50 rating | bar: Wk15
5 · Interior | Bathroom tile + fixtures | Tiler + Plumber | 3 | MED | Bathroom center | W/D connection finalise | bar: Wk1 to Wk22
5 · Interior | Interior doors + hardware | Carpenter | 2 | MED | All rooms | Match existing door profiles | bar: Wk16
5 · Interior | Cabinetry – kitchen | Cabinet maker | 2 | MED | Kitchen | After new floor assembly complete | bar: Wk1 to Wk22
5 · Interior | Paint – all interior | Painter | 3 | MED | All rooms | After drywall tape + mud dry | bar: Wk16 to Wk17
5 · Interior | Stair finishing – central stair | Carpenter | 2 | MED | Central stair | Existing stair – refinish treads | bar: Wk1 to Wk22
5 · Interior | Living room + dining fit-out | GC / Carpenter | 2 | MED | East zones | After new window + beam complete | bar: Wk17
5 · Interior | Electrical trim-out + panel | Electrician | 2 | HIGH | All rooms | Panel energise after inspection | bar: Wk1 to Wk22
5 · Interior | HVAC trim-out + commission | HVAC | 2 | MED | All rooms | Test all zones | bar: Wk18
5 · Interior | Parking level finish – concrete seal | Concrete | 2 | LOW | West parking | Seal parking deck surface | bar: Wk1 to Wk22
6 · Close-Out | Final clean – full building | GC | 3 | HIGH | All | All trades complete first | bar: Wk19
6 · Close-Out | Fire rating inspections | Inspector / GC | 2 | CRIT | Garage + parking | 1½ hr ceiling, gas-proof, STC 50 | bar: Wk1 to Wk22
6 · Close-Out | Structural engineer final sign-off | SE / GC | 1 | CRIT | All structural | All beams/posts per design confirmed | bar: Wk20
6 · Close-Out | Punchlist + defects | GC + all trades | 4 | HIGH | All | Owner walkthrough | bar: Wk1 to Wk22
6 · Close-Out | Certificate of Occupancy | Inspector / GC | 1 | CRIT | Full building | Final CO – all systems commissioned | bar: Wk22

## SpatialFlow Input
SPATIALFLOW SPATIAL LAYOUT INPUT — Renovation Plan (68'-2" × 43'-0")
⚠ RENOVATION CONSTRAINT: Existing porch (East), fire-escape stairs (SE), concrete stair (E), steel guard — ALL MUST REMAIN. Route all materials to avoid these zones.
Week | Phase | Activity | Materials Arriving | Volume | Work Zone | Equipment | Storage Zone | Conflict Risk | Spatial Priority Note
1 | Pre-Con | Hazmat survey | Test equipment only | Negligible | Full interior | None | N/A – survey only | CRIT | ALL rooms accessed. Building empty. No storage conflict.
1 | Pre-Con | Structural assessment | None | None | Beam/post locations | None | N/A | CRIT | Engineer must access all 3 parking levels + dining beam
2 | Pre-Con | Temp protection – east | Hoarding boards, tarps | Low | East porch + SE stairs | Pickup | East perimeter – install | HIGH | East porch + fire escape stairs: NO access. Hoarding marks exclusion zone
3 | Demo | Kitchen stair removal | None – debris out | High debris | Kitchen NE | Skip/dumpster | Dumpster: North access road | HIGH | Debris route: kitchen → north corridor → North dumpster. Keep East clear
3 | Demo | Close-up window openings | Face brick, mortar, lintels | Medium | Bedroom 1+2 facade | Scaffold (2-lift) | North facade staging | HIGH | Scaffold N facade. Brick must match – store samples on site
3 | Demo | Hazmat abatement | Containment barriers, PPE | Low | As identified | Negative pressure unit | Adjacent to abatement zone | CRIT | STOP WORK ZONE during abatement. Full site access halted in affected area
4 | Demo | Remove dining beam | Temp shoring (acrow props) | Medium | Dining – East | Acrow props | Dining zone – props in place | CRIT | Temp shoring BEFORE beam removal. Props remain until Parallam installed
4 | Demo | Remove SE brick post | None – debris out | Low debris | South-East corner | Skip | SE corner – small skip | MED | Small area. Existing foundation stays. Protect adjacent fire-escape stair
5 | Structure | Parallam beam – dining | 3½×9½" Parallam beam (heavy) | High | Dining | Crane / boom truck | North staging – beam length | CRIT | Long beam – needs clear North access. Temp shores stay until beam seated+connected
5 | Structure | Timberstrand beam – porch | 2-1 3/4×11 7/8" Timberstrand | High | NW porch | Crane | North-West staging | CRIT | Crane North-West. Must not swing over East exclusion zone
5 | Structure | HSS steel post | 3.5" HSS steel post + plates | Medium | West parking level | Crane / fork | West staging | HIGH | Steel post heavy. Base plate: 4×4×½". Crane reach to West levels
6 | Structure | TJI joists – parking | 11 7/8" TJI bundles | High | West parking levels | Crane | West staging – stacked | HIGH | Joists long – West staging must be clear 20ft. Crane active all week
6 | Structure | Concrete block – parking wall | CMU 8" block pallets | Very High | West parking | Forklift | West – staged by level | HIGH | Heaviest material. Forklift accesses West side only. No East access this week
6 | Structure | Kitchen ledger + bolts | 2×10 lumber, 1½" dia bolts | Low | Kitchen NE | None | Inside kitchen | MED | Small material. Store inside. Bolt pattern per plan – staggered 2 rows
9 | Exterior | Kitchen floor assembly | Joists, decking, fire materials | Medium | Kitchen | None | Inside kitchen zone | HIGH | Fire-rated assembly – materials must be certified. Inspect before close-up
9 | Exterior | Face brick – bedrooms | Brick pallets (match existing) | High | N facade – bed 1+2 | Scaffold | North facade – adjacent | HIGH | Brick colour/texture match critical. Order samples week 1. Stage North only
10 | Exterior | New windows – all | Window units (3) | Medium | N + E facades | None / small crane | North staging – protected | MED | Windows fragile. Deliver just-in-time. North facade access only
10 | Exterior | New concrete stairs – E porch | Ready-mix concrete | Low | East covered porch | Concrete pump | East porch zone | HIGH | ONLY concrete work near East exclusion zone. Protect existing porch structure
10 | Exterior | New brick post – SE | Face brick, mortar, rebar | Low | South-East corner | None | SE corner – small staging | HIGH | Build on existing foundation. Fire-escape stair adjacent – do NOT disturb
11 | Exterior | Garage slab patch | Ready-mix concrete (small) | Low | Garage – South-West | None | Garage interior | MED | Maintain 1% slope to front. Gas-proof ceiling must remain intact above
11 | Exterior | Gas-proof ceiling – garage | Type X drywall, intumescent | Medium | Garage ceiling | None | Garage interior | CRIT | Gas-proof rating must be maintained. Inspector sign-off before next phase
11 | Exterior | Guard rails – porch | Steel / timber rail components | Medium | NW porch | None | NW porch area | HIGH | 3'-6" high guard. Install after beam and post confirmed plumb and level
13 | MEP | Plumbing rough-in | PVC/copper pipe, fittings | Medium | Bathroom + W/D zone | None | Inside – bathroom zone | MED | W/D hookup adjacent bathroom. Coordinate drain with existing slab penetrations
13 | MEP | Electrical rough-in | Wire, conduit, panel gear | Medium | All rooms | None | Inside – locked storage | HIGH | Panel upgrade likely. Coordinate with fire-rated ceiling zones in parking/garage
14 | Interior | Insulation – fire rated | 1½ hr rated insulation + board | Medium | Parking + garage ceil | None | Inside – staging by zone | CRIT | C1 type ceiling insulation. Do not substitute. Inspector to verify
14 | Interior | Drywall – all rooms | Drywall sheets (type X zones) | High | All interior | None | Inside – room by room | HIGH | Type X for garage + parking fire-rated areas. Standard elsewhere
15 | Interior | Kitchen floor finish | Flooring, adhesive, underlayment | Medium | Kitchen | None | Inside kitchen | HIGH | STC 50 + 45min fire. Use specified assembly – no substitution
15 | Interior | Bathroom tile + W/D | Tile, grout, W/D unit | Medium | Center bathroom | None | Inside bathroom | MED | W/D connection: verify rough-in clearances before delivery
16 | Interior | Paint all rooms | Paint, primer, drop sheets | Low | All rooms | None | Inside – cool ventilated | HIGH | Flammable – ventilated storage. No energising in storage room
19 | Close-Out | Fire rating inspections | None | None | Garage + parking | None | N/A | CRIT | Inspector verifies: 1½ hr ceiling, gas-proof garage, STC 50 kitchen floor
22 | Close-Out | Certificate of Occupancy | None | None | Full building | None | N/A | CRIT | All systems commissioned. Engineer + inspector sign-off required

## Spatial Conflict Register
SPATIAL CONFLICT RISK REGISTER — Renovation Plan
Renovation conflicts are more complex than new builds — existing protected elements + live structural work create unique spatial risks
Week | Conflict Type | Element A | Element B | Zone | Severity | Resolution
3 | Demo + protected zone | Demo crew (kitchen stair) | East porch + fire-escape (REMAIN) | East transition zone | CRITICAL | Hoarding wall between demo zone and East protected elements. Daily check
3 | Hazmat stop-work | All trades on site | Hazmat abatement zone | As identified | CRITICAL | If hazmat found: full stop-work in affected area. Quarantine zone established immediately
4 | Shoring + access | Acrow props (temp shoring) | All traffic through dining zone | Dining – East | HIGH | Prop positions limit access. Mark clearly. No loads placed near props during beam removal
5 | Crane swing arc | Crane (Parallam beam lift) | East exclusion zone (porch/stair) | North to dining | CRITICAL | Crane must NOT swing over East zone. Lift path: North → West → dining only. Banksman required
5 | Two-beam week | Parallam beam (dining) | Timberstrand beam (NW porch) | N + NW staging | HIGH | Two heavy beam deliveries same week. Sequence: Parallam Mon, Timberstrand Thu. Separate crane setups
6 | Block + joist congestion | CMU block pallets (West) | TJI joist bundles (West) | West staging | HIGH | Both heavy – West staging only. Sequence: joists first (lifted to level), then block staged below
9 | Scaffold + facade access | Face brick scaffold (N facade) | Window deliveries (N facade) | North facade | HIGH | Scaffold gaps designated for window pass-through. Windows delivered before scaffold fully erected
10 | Concrete + exclusion zone | Concrete pump (East porch stairs) | East exclusion zone (fire escape) | East side | CRITICAL | Concrete pump positioned North-East. Chute reaches East porch. Fire-escape stair barriered – no concrete contact
10 | Brick post + fire escape | New brick post construction (SE) | Existing fire-escape stairs (SE) | South-East corner | HIGH | 12"×12" post on existing fdn. Scaffold for post must not block fire-escape path at any time
11 | Gas-proof + active trades | Garage ceiling repair (gas-proof) | Electrical rough-in (garage) | Garage | CRITICAL | Gas-proof ceiling must be complete before electrician works in garage. Sequenced: ceiling → inspection → electrical
13 | MEP + fire-rated zones | Electrical rough-in | Fire-rated ceiling (parking) | West parking levels | HIGH | Electrical penetrations through fire-rated ceiling require fire-stopping. Specify before rough-in begins
14 | Drywall + fire rating | Standard drywall crew | Type X zones (garage/parking) | Garage + W parking | CRITICAL | Type X must be used in rated zones. GC to mark all sheets before delivery. Inspector to verify before taping
15 | Kitchen floor rating | Flooring crew (kitchen) | STC 50 + 45min fire assembly | Kitchen | CRITICAL | Specified assembly only. Any substitution voids fire rating. Inspector to verify assembly before topping
17 | Paint + panel energising | Paint storage (flammable) | Electrical panel energising | All interior | CRITICAL | Paint completely removed from interior before panel energised. No exceptions – fire risk
19 | Multi-inspection week | Fire inspector | Structural engineer sign-off | Garage + parking + all structural | HIGH | Coordinate both inspections same week. GC to pre-submit all documentation 1 week prior

## Fire Rating Tracker
FIRE RATING COMPLIANCE TRACKER — Critical for This Renovation
This plan has multiple fire-rated assemblies. Each must be inspected and signed off before close-up.
Location | Required Rating | Assembly Type | Inspection Week | Sign-Off Required | Notes from Plan
Garage ceiling | 1½ hr | C1 Type ceiling | 11 + 19 | Inspector + GC | R27 min in ceiling – gas-proof ceiling and walls throughout
Parking level ceiling | 1½ hr | C1 Type fire-rated ceiling | 14 + 19 | Inspector + GC | R27 min in ceiling above parking – same as garage
Garage walls | Gas-proof | 8" conc. block, design B1b, SG-8 | 11 + 19 | Inspector | Gas-proof wall as per design B1b from SG-8 for 1½ hr fire rating
Kitchen floor assembly | 45 min | Floor assembly per Design No. F4a | 15 + 19 | Inspector + SE | New floor assembly to achieve 45 min fire rating & STC 50
Kitchen floor (acoustic) | STC 50 | Per Design No. F4a | 15 + 19 | Inspector | Both fire and acoustic rating required – same assembly
Bedroom windows | Face brick | 8" face brick – 45 min fire | 10 + 19 | Inspector | 8" face brick exterior wall – good for 45 min fire rating per plan note
Parking block wall | 1 hr | 8" conc. block, SG-8 spec | 8 + 19 | SE + Inspector | Design B1b – professional structural engineer check required
Garage door opening | Fire-rated dr | 20-min or 45-min rated door | 19 | Inspector | Garage door must be fire-rated – verify with AHJ